## Sheet1
Deliverable | Author | Reviewed By | Comments
|  |  | Issue | Date | Status | Issue | Date | Status | Issue | Date | Status | Issue | Date | Status | Issue | Date | Status
Project Plan | Nesma Bahgat | Asmaa Hamdy | 1-In the project goals and objectives section:- they are more likely a “product” goals not project goals 2-In The Constraints section:- the constraints are more likely to be risks and issues rather than being constraints 3-In the roles section:- The product owner is only Eng. Marwan not Eng. Muhammad Hassan | 2019-01-05 | Accepted
Project Schedule | Maysoon Magdy | Esraa Salah | 1- Review the start dates and finish dates with the team members. 2- Rename the section of 'work' to 'work hours'. 3- The Completed percentage section calculations is incorrect. 4- Move the question marks displayed after the number of days from the 'duration' section. 5- The extension of 'TAWA_SIQ 'document is '.xlsx 'not '.docx'. 6- Add the' TAWA_SystemRequirements.xlsx' document and 'TAWA_CustomerRequirements.xlsx' document to the documents section. 7- The PDF version contents of the 'project schedule' document are overlapping . | 2019-01-05 | Accepted
CM Tool | Asmaa Hamdy | Sara Sayed | 1- Edit section 2.1: change “GitHub tool” to “GitHub Desktop tool”. 2- Edit section 2.2: change “development team” to “delivery team”. 3- Mention the documents branch in section 2.2 . | 2019-01-05 | Accepted
Risk Sheet | Mahmoud Yasser | Maysoon Madgy | 1-TAWA_Rsk1 is project (organizational) risk not product. 2-I think that we should but a range like (10-15 --> high risk) to explain our risk categorization. 3-Add (A system may not satisfy the customer) ---> product risk 4-TAWA_Rsk8 ---- use (instant messaging && desktop sharing) in mitigation as agile terminologies instead of social media. | 2019-01-05 | Accepted
Issues sheet | Mahmoud Yasser | Nesma Bahgat | We faced another issue which is the first time for the whole team to make a whole project with its back-end and front-end, which may impact in the velocity to finish the implementation of the project and may affect also in in finishing the rest activities in the project. | 2019-02-05 | Accepted
SRS | Sara Sayed | Mahmoud Yasser | 1 – Add restriction on booking a flight function (only 1 flight for every user) 2- Search function for Admin user is out of scope 3- Update Non-Functional requirements and remove security, compatibility, maintainability, reliability, portability, and usability. 4- Update Constraints: Java instead of C# and ASP.NET | 29/4/2019 | Accepted | 1) in section 2.2 Roles U-1, U-2, and U-3 : No Activation needed for user 2) TAWA_SRS_FR_016 AND TAWA_SRS_FR_066 : email field can contain characters or a combination of characters and numbers before '@' 3) TAWA_SRS_FR_134 : Not testable. | 2019-10-05 | Accepted
SIQ | Esraa Salah | Sara Sayed | 1- TAWA_SIQ_007 add the length of password field. 2- Ask a question to specify the length of the phone number field. | 29/4/2019 | Accepted
RTM | Nesma Bahgat | Sara Sayed & Esraa Salah | 1-Add SIQ column in the table | 29/4/2019 | Accepted
HLD (Design Document) | Mahmoud Yasser | Nesma Bahgat | 1-Payment Method doesn't exist in the diagaram. 2-Add HTTP server | 2019-05-10 | 1- Accepted 2- Rejected : Not necessary
Wireframes | Nesma Bahgat | Asmaa Hamdy | 1- Add show details button to each trip 2- The content of the side-bars doesn't exist The following screens don't exist:- 3- What will the user see after submitting the flight? 4- Where will the user be directed to after signing-up? | 2019-10-05 | Accepted
Usecase Diagram | Maysoon Magdy | Saya Sayed | 1- Add usecase for view all users. 2- Add usecase for Edit users. 3- 'login' usecase include from 'sign up' usecase. 4- Add two usecases 'cash' and 'debit card' and both extend from 'payment' usecase. 5- make 'show destination details' include from 'land on photo gallery' usecase. 6- make 'explore different airlines' and 'choose payment method' usecase include from 'book flight' usecase. 7- Add usecase For each airline extend from 'explore different airlines' usecse. | 2019-10-05 | Accepted
Admin Module (UI) | Asmaa Hamdy | Nesma Bahgat | 1-Change add user Page style. 2-In admin page, replace the (edit,delete) buttons at the end of the users name list with 2 buttons for add &delete beside each user name. | 2019-05-16 | Accepted
Login Module (UI) | Maysoon Magdy | Nesma Bahgat | 1-change Backgroung. | 2019-05-16 | Accepted
Sign up Module (UI) | Maysoon Magdy | Nesma Bahgat | 1-Change size of page. 2-Add required Validation to the page. | 2019-05-16 | Accepted
Destination Details Module (UI) | Maysoon Magdy | Nesma Bahgat | 1-Remove feedbacklink from Header. 2-Remove the extra Header as there is 2 headers in the page | 2019-05-16 | Accepted
Home Page Module(UI) | Nesma Bahgat | Asmaa Hamdy | 1-Change Font in page. | 2019-05-15 | Accepted
Booking Module (UI) | Nesma Bahgat | Asmaa Hamdy,Sara Sayed | 1-Change Font in page. 2-Field debit Card number should appear only in case user choose debit card as a payment Method | 2019-05-15 | 1- Accepted 2- Rejected : It is done in different way
Feedback and Rating Module (UI) | Nesma Bahgat | Esraa Salah | 1- Stars in Rating is just an image and it must retreive data. | 2019-05-15 | Accepted
Reserved Trips Module (UI) | Asmaa Hamdy
Data Base (BackEnd) | Mahmoud Yasser
Admin Module (BackEnd) | Sara Sayed
Login Module (BackEnd) | Esraa Salah
Sign up Module (BackEnd) | Esraa Salah
Destination Details Module (BackEnd) | Esraa Salah
Home Page Module(Back End) | Esraa Salah
Booking Module (BackEnd) | Esraa Salah
Feedback and Rating Module (BackEnd) | Esraa Salah
Reserved Trips Module (BackEnd) | Esraa Salah
Admin Module (Test Cases) | Asmaa Hamdy
Login Module (Test Cases) | Nesma Bahgat
Sign up Module (Test cases) | Nesma Bahgat
Destiantion Details (Test Cases) | Maysoon Magdy
Home Page (Test Cases) | Maysoon Magdy
Feedback and rating (Test Cases) | Maysoon Magdy
Reserved Trips (Test Cases) | Mahmoud Yasser
Booking Module(Test Cases) | Mahmoud Yasser
Page Header (Test Cases) | Mahmoud Yasser